## WBS with Gantt Chart
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE | [6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception & Initiation
1.1 | Brain Storming | all | 2019-02-08 | 2019-02-08 | 1 | 100%
1.1.1 | 아이디어 구상 | all | 2019-02-08 | 2019-02-08 | 1 | 100%
1.2 | 아이디어 구체화 및 요구사항 분석 | all | 2019-02-08 | 2019-02-08 | 1 | 90%
1.2.1 | 역할 분담 | all | 2019-02-08 | 2019-02-08 | 1 | 90%
2 | 구현 계획
3.1 | 노트북 기능 구현 | 임수연 | 2019-02-08 | 2019-02-17 | 10 | 0%
3.2 | 노트 기능 구현 | 정주원 | 2019-02-08 | 2019-02-17 | 10 | 0%
3.2.1 | DB를 사용한 노트 저장 기능 구현 | 임수연 | 2019-02-18 | 2019-02-25 | 8 | 0%
3.2.2 | 검색 기능 구현 | 정주원 | 2019-02-18 | 2019-02-25 | 8 | 0%
3.3 | Project Updates | Pete S |  |  | 0 | 0%
3.3.1 | Chart Updates | Malik M |  |  | 0 | 0%
4 | 제작 계획
4.1 | 태그 기능 구현 | 임수연 | 2019-02-26 | 2019-02-27 | 2 | 0%
4.2 | 바로가기 기능 구현 | 정주원 | 2019-02-26 | 2019-02-27 | 2 | 0%
4.3 | 휴지통 기능 구현 | 임수연, 정주원 | 2019-02-28 | 2019-03-01 | 2 | 0%
4.4 | 완성
4.3 | 어플리케이션 테스트 | 임수연, 정주원 | 2019-03-01 | 2019-03-01 | 1 | 0%
4.3 | 버그 수정 및 개선 | 임수연, 정주원 | 2019-03-01 | 2019-03-03 | 3 | 0%
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
DURATION = DAYS([DUE DATE],[START DATE])+1
DURATION = DAYS([DUE DATE],[START DATE])

## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE | [6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.